## Gantt
GreenCode final-year project plan
| Week 1 starts on |  | 2026-09-14
| Current week |  | 5
Blue cells are inputs you can edit. Bars, dates and statuses are formulas.
[9 empty] | Sep 26 |  |  | Oct 26 |  |  |  | Nov 26 |  |  |  |  | Dec 26 |  |  |  | Jan 27 |  |  |  | Feb 27 |  |  |  | Mar 27 |  |  |  |  | Apr 27
# | Phase | Task | Start wk | End wk | Start date | End date | Weeks | Status | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
1 | Research | Literature review and reference library | 1 | 8 | 2026-09-14 | 2026-11-06 | 8 | In progress
2 | Research | Project proposal: research question, hypotheses, approach | 3 | 6 | 2026-09-28 | 2026-10-23 | 4 | In progress
3 | Requirements | Requirements gathering and user-group feedback | 4 | 7 | 2026-10-05 | 2026-10-30 | 4 | In progress
4 | Analysis & design | Architecture, database schema, UML diagrams | 5 | 8 | 2026-10-12 | 2026-11-06 | 4 | In progress
5 | Implementation | Core pipeline: analysis, AI generation, verification, benchmark | 6 | 10 | 2026-10-19 | 2026-11-20 | 5 | Planned
6 | Research | Interim report | 8 | 10 | 2026-11-02 | 2026-11-20 | 3 | Planned
7 | Implementation | Energy and CO₂e measurement layer; admin panel | 10 | 13 | 2026-11-16 | 2026-12-11 | 4 | Planned
8 | Implementation | Expand benchmark suite to 30–50 cases | 11 | 14 | 2026-11-23 | 2026-12-18 | 4 | Planned
9 | Testing & evaluation | Pilot experiment runs and fixes | 13 | 14 | 2026-12-07 | 2026-12-18 | 2 | Planned
10 | Break | Christmas break and semester 1 exams | 15 | 19 | 2026-12-21 | 2027-01-22 | 5
11 | Analysis & design | Dashboard polish and Nielsen heuristic audit | 20 | 21 | 2027-01-25 | 2027-02-05 | 2 | Planned
12 | Implementation | Hardening, bug fixes and documentation | 20 | 22 | 2027-01-25 | 2027-02-12 | 3 | Planned
13 | Testing & evaluation | Full experiment runs under both conditions | 22 | 26 | 2027-02-08 | 2027-03-12 | 5 | Planned
14 | Testing & evaluation | Statistical analysis and failure analysis | 26 | 28 | 2027-03-08 | 2027-03-26 | 3 | Planned
15 | Research | Dissertation writing | 24 | 31 | 2027-02-22 | 2027-04-16 | 8 | Planned
16 | Testing & evaluation | Final review, demonstration and submission | 31 | 32 | 2027-04-12 | 2027-04-23 | 2 | Planned
17 | Testing & evaluation | Unit and integration tests (continuous) | 6 | 30 | 2026-10-19 | 2027-04-09 | 25 | Planned
Milestones
|  | Interim report due | 10 | 10 | 2026-11-20 | [12 empty] | ◆
|  | Semester 1 ends | 14 | 14 | 2026-12-18 | [16 empty] | ◆
|  | Semester 2 starts | 20 | 20 | 2027-01-29 | [22 empty] | ◆
|  | Final submission (late April) | 32 | 32 | 2027-04-23 | [34 empty] | ◆
Legend
Research
Requirements
Analysis & design
Implementation
Testing & evaluation
Break
Current week
◆ Milestone
Dates assume TU Dublin semester 1 teaching ends week 14, semester 2 begins week 20, and final submission is Friday 30 April 2027 (week 32). Edit D2 or any start/end week to replan.
Note on D3: Change this each week. Status column and the orange column highlight update automatically.